QA ENGINEER
CAREER TRANSITION PLAN

From No Professional Experience to Job-Ready QA Candidate

10-Week End-to-End Roadmap — Hireability-Reviewed Edition

Start date: September 15, 2026  |  Target completion: November 22, 2026

Starting point • Master's degree in Computer Science completed in 2018 • No professional software QA work experience yet • Already exposed to QA concepts and Playwright through videos • Primary goal: obtain the first professional software QA role

The strategy: reduce passive study, build proof of ability, create legitimate external evidence where possible, and apply before everything feels perfect.

# How to Use This Plan

Core principle Your degree gives you academic credibility. The missing piece is recent, visible, hands-on QA evidence. Every week in this plan creates something you can show, explain, or use in an interview.

This plan is designed around approximately 2-3 focused hours per day, 5-6 days per week. If you have more time, compress it. If you have less time, keep the sequence and extend the dates.

## The five rules

1. Build more than you watch. For every hour of videos, aim for at least two hours of hands-on practice.

2. Keep one main portfolio project for depth, then add one small independent assessment later to prove you can transfer the skills to an unfamiliar application.

3. Do not invent employment history, job titles, clients, or years of experience. Use real project work instead.

4. Start applying in Week 4. Do not wait until Week 10 to discover what employers are asking for.

5. Track outcomes. Applications, recruiter responses, interviews, rejections, and skill gaps are data that should change your approach.

## What success looks like by November 22, 2026

[ ] One polished end-to-end QA portfolio project on GitHub.

[ ] 40-50 original manual test cases plus smoke and regression subsets.

[ ] 8-10 well-written bug reports based on observed or clearly labeled practice defects.

[ ] Approximately 20 API tests in Postman, including positive and negative scenarios.

[ ] 15-25 Playwright tests covering meaningful user flows, not only trivial selectors.

[ ] Comfort with practical SQL queries used for test-data and database verification.

[ ] Basic CI execution for Playwright tests through GitHub Actions.

[ ] A one-page QA resume, a credible LinkedIn profile, and a clean GitHub README.

[ ] An active application system with interview practice already underway.

[ ] A baseline one-page resume and LinkedIn profile ready before the first applications in Week 4.

[ ] One small independent QA assessment on a second application, separate from the primary tutorial/practice project.

[ ] Working JavaScript/TypeScript fundamentals sufficient to read, write, and debug Playwright tests without copying a tutorial.

## Hireability Review: What Was Strengthened

This edition was reviewed specifically for the question: “Does this give a zero-experience candidate the strongest realistic chance of getting hired?” The core roadmap remains 10 weeks, but several gaps were corrected.

• Resume/LinkedIn creation now happens before applications begin, not several weeks afterward.

• Programming and debugging fundamentals are now part of the core stack, because automation roles commonly expect real coding fluency—not only recorder-style test scripts.

• Browser DevTools and failure diagnosis are included so you can investigate problems rather than only report symptoms.

• A small second project is added to show independent thinking outside the main practice application.

• The job-search section now filters out senior SDET roles more aggressively and adds contract/project-hire and legitimate crowdtesting as optional experience bridges.

• Resume optimization in Week 9 is now an iteration step based on market feedback, not the first time you create a resume.

# Contents

1. Role Strategy and Skill Priorities

2. 10-Week Roadmap at a Glance

3. Daily Study and Practice Routine

4. Week-by-Week Execution Plan

5. Complete Portfolio Project Specification

6. Resume, LinkedIn, and Career-Gap Positioning

7. Job Search System

8. Interview Preparation System

9. Progress Checkpoints and Troubleshooting

10. What to Learn Later

11. Final Job-Ready Checklist

12. Reference Resources

# 1. Role Strategy and Skill Priorities

Primary target roles: QA Engineer, Software QA Engineer, QA Analyst, Software Tester, Test Engineer, Junior QA Engineer, Associate QA Engineer, and selected junior automation roles.

Important title warning Search results for “Quality Engineer” often include manufacturing, supplier quality, hardware inspection, or regulated-product quality roles. Read the job description and confirm the work is software testing before applying.

## September 2026 market calibration

Current Bay Area automation postings repeatedly combine UI automation with API testing, SQL/database validation, CI/CD, Git, debugging, and a programming language. Many of those openings are senior, which is exactly why this plan does not tell you to chase every Playwright/SDET listing. Your goal is to build the same foundational skill pattern at an entry-level depth and target roles whose ownership and experience requirements are realistic.

Use this rule: match the work, not just the title. A “QA Engineer” posting can still be senior; a “Test Engineer” or project-hire posting may be more realistic. Read responsibilities and years/ownership requirements before applying.

## Must-have stack for the first role

| Area | What you need | Priority |
| --- | --- | --- |
| Manual QA | Test design, functional testing, regression, smoke, exploratory testing, bug reporting | High |
| API Testing | Postman, REST, JSON, HTTP methods/status codes, positive/negative tests | High |
| SQL | SELECT, WHERE, JOIN, GROUP BY, COUNT, data verification | High |
| Automation | Playwright + TypeScript/JavaScript, locators, assertions, fixtures, test data, debugging | High |
| Version Control | Git, GitHub, branches, commits, pull requests | Medium |
| CI basics | Run automated tests in GitHub Actions | Medium |
| Process | Agile/Scrum, SDLC/STLC, defect lifecycle | Medium |
| Programming | JavaScript/TypeScript fundamentals: functions, arrays/objects, modules, async/await, error handling, npm | High |
| Diagnostics | Browser DevTools: Console, Network, request/response inspection, storage basics, reading stack traces/log output | High |

## Role filter: what to apply to vs. skip

Apply aggressively when the role centers on functional testing, test cases, bug reporting, API/SQL basics, web testing, or maintainable automation and asks for 0-2 years or uses flexible experience language. Also include contract, temporary, project-hire, and hybrid manual/automation QA roles.

Usually skip roles labeled Senior, Staff, Lead, Principal, or Manager; roles requiring 4-5+ years as a hard requirement; roles asking you to architect an enterprise framework from scratch; and SDET roles where advanced coding/algorithms are central. A 1-2 year preference is not an automatic rejection if the rest of the work is plausibly junior.

Do not rely on internships unless you confirm you meet their student/new-graduate eligibility rules.

## Do not make these your priority yet

Advanced Java or C#

Appium/mobile automation

Performance engineering/JMeter

Docker/Kubernetes

Cloud certifications

Advanced DevOps

Security penetration testing

Complex data structures and algorithm preparation

These skills can help later, but they should not delay your first applications.

# 2. 10-Week Roadmap at a Glance

| Week | Dates | Focus | Outcome | Main Deliverable |
| --- | --- | --- | --- | --- |
| 1 | Sep 15-20 | Manual QA foundations | Explain core concepts and begin application exploration | QA notes + 15 scenarios |
| 2 | Sep 21-27 | Test design | Turn requirements into systematic test coverage | 40-50 test cases + smoke/regression sets |
| 3 | Sep 28-Oct 4 | Defects + exploratory testing + DevTools | Write reproducible bugs, investigate failures, and prepare a baseline resume/profile | Bug reports + exploratory notes + baseline resume/LinkedIn |
| 4 | Oct 5-11 | SQL + coding foundation + first applications | Verify data, strengthen TypeScript/JavaScript fundamentals, and start market feedback | SQL repo + coding exercises + 5-10 applications |
| 5 | Oct 12-18 | API/Postman | Validate REST services independently of UI | ~20 API tests + exported collection |
| 6 | Oct 19-25 | Playwright + programming/debugging | Automate stable flows and explain the code/failures | 8-12 reliable tests + debugging notes |
| 7 | Oct 26-Nov 1 | Automation framework | Organize maintainable tests and debugging evidence | 15-25 tests + page objects where useful |
| 8 | Nov 2-8 | GitHub + CI + independent mini-project | Make the main project recruiter-readable and prove skill transfer | README + GitHub Actions + mini QA assessment |
| 9 | Nov 9-15 | Resume/LinkedIn optimization + application ramp | Use real response data to improve packaging and targeting | Two truthful resume variants + 25-40 applications/week pace |
| 10 | Nov 16-22 | Interview sprint | Convert applications into confident interviews | Mock interviews + targeted gap fixes |

Application timing Begin light applications in Week 4. Increase the volume as the portfolio becomes stronger. The goal is to learn from the market while you are still improving, not after you finish studying.

# 3. Daily Study and Practice Routine

Use this default 2-3 hour block:

| Time | Activity | What to do |
| --- | --- | --- |
| 20 min | Review | Recall yesterday's concepts without notes. Explain them aloud. |
| 30-40 min | Focused learning | Read documentation or study only the material needed for today's task. From Week 4 onward, include JavaScript/TypeScript coding practice several days per week. |
| 75-100 min | Hands-on work | Write test cases, run Postman, write SQL, automate with Playwright, debug failures. |
| 15 min | Documentation | Commit work to Git, update README/test evidence, record what you learned. |
| 10 min | Interview/debug recall | Answer 2-3 interview questions aloud or explain one failure/stack trace without reading an answer. |

## Weekly rhythm

Days 1-4: learn and build.

Day 5: finish the weekly deliverable and clean the documentation.

Day 6: review, interview practice, GitHub cleanup, and applications.

Day 7: optional rest or light review. Avoid turning every day into passive video consumption.

# 4. Week-by-Week Execution Plan

## Week 1 (Sep 15-20): Manual QA Foundations

Objective Move from “I have watched QA videos” to “I can explain the testing process and identify what needs to be tested.”

### Topics to master

SDLC and STLC

Requirement analysis

Test scenario vs. test case

Positive vs. negative testing

Functional vs. non-functional testing

Smoke, sanity, and regression testing

Exploratory testing

Severity vs. priority

Defect lifecycle

Agile/Scrum basics: sprint, backlog, story, acceptance criteria, daily stand-up

### Hands-on tasks

[ ] Open the chosen practice application and map its major features: registration, login, products, cart, checkout, contact, account management.

[ ] Write at least 15 high-level test scenarios without copying an existing test-case list.

[ ] For each feature, identify one positive path, one negative path, and one edge case.

[ ] Create a glossary document in your repository and explain each core QA term in your own words.

### Week 1 exit criteria

[ ] Can explain smoke vs. sanity vs. regression without notes.

[ ] Can explain severity vs. priority with examples.

[ ] Can look at a login page and quickly produce at least 15 useful test ideas.

[ ] Has 15+ original scenarios committed to GitHub or saved in the project folder.

## Week 2 (Sep 21-27): Test Design and Coverage

Objective Create professional test assets that show systematic thinking, not random clicking.

### Test-design techniques

Equivalence partitioning

Boundary-value analysis

Decision-table thinking

State-transition thinking

Error guessing

Risk-based prioritization

### Build your manual suite

[ ] Create 40-50 detailed test cases across registration, authentication, product search, cart, checkout, forms, and account management.

[ ] Mark 8-12 critical cases as the smoke suite.

[ ] Create a regression subset of approximately 25 high-value tests.

[ ] Include normal, invalid, blank, boundary, and state-dependent cases.

[ ] Execute the cases and record Actual Result plus Pass/Fail rather than leaving the sheet theoretical.

### Recommended test-case columns

| Field | Purpose |
| --- | --- |
| Test Case ID | Stable identifier such as TC-LOGIN-001 |
| Feature/Scenario | What is being tested |
| Preconditions | Required state before execution |
| Steps | Numbered actions |
| Test Data | Inputs used |
| Expected Result | Observable correct behavior |
| Actual Result | What happened |
| Status | Pass / Fail / Blocked |
| Priority | High / Medium / Low |
| Notes/Evidence | Screenshot, browser, special observations |

## Week 3 (Sep 28-Oct 4): Defect Reporting and Exploratory Testing

Objective Show that you can communicate a defect clearly enough for a developer to reproduce and fix it.

[ ] Perform structured exploratory sessions of 30-45 minutes. Pick one area, define a charter, test it, and record observations.

[ ] Create 8-10 bug reports. Prefer real observed behavior. If you use a hypothetical practice defect, label it clearly as a practice example.

[ ] Attach evidence where useful: screenshot, short video, console/network note, or exact test data.

[ ] Practice assigning severity and priority separately, and explain your reasoning.

### Browser diagnostics basics

[ ] Use Chrome/Edge DevTools Console to notice JavaScript errors and warnings.

[ ] Use the Network tab to inspect request URL, method, status, payload, and response for at least five actions.

[ ] Know where cookies/local storage/session storage can be inspected, without changing production data or bypassing access controls.

[ ] For two defects or suspicious behaviors, record what the UI showed and what the network/console evidence showed.

### Baseline resume and LinkedIn — before applications

[ ] Create a truthful one-page baseline resume using your degree, current QA skills, and project work completed so far. Do not wait for the portfolio to be finished.

[ ] Update LinkedIn headline/About to reflect a transition into software QA and the skills you can already demonstrate.

[ ] Add GitHub/portfolio links even if the repository is still evolving.

[ ] Prepare a 30-second introduction so a surprise recruiter call does not arrive before your story is ready.

### Bug-report template

| Field | What good looks like |
| --- | --- |
| Bug ID | BUG-001 |
| Title | Specific: action + condition + incorrect result |
| Environment | Browser/OS/build or relevant setup |
| Preconditions | State required to reproduce |
| Steps | Short, numbered, deterministic |
| Expected | What should happen |
| Actual | What actually happens |
| Severity | Impact on system/user |
| Priority | Urgency to fix |
| Evidence | Screenshot/video/logs where appropriate |

Quality test A developer who has never seen your test session should be able to reproduce the bug from your report without asking what you meant.

## Week 4 (Oct 5-11): SQL + Start Applying

Objective Learn enough SQL to validate application data and begin getting real market feedback.

### SQL topics

SELECT and column selection

WHERE with multiple conditions

ORDER BY

DISTINCT

COUNT and basic aggregates

GROUP BY and HAVING

INNER JOIN

LEFT JOIN

NULL handling

Simple subqueries

Basic awareness of INSERT/UPDATE/DELETE, with caution on test data

### Practice outcomes

[ ] Create a small sample database or use an online SQL practice environment.

[ ] Write at least 25 queries yourself, including 8-10 JOIN queries.

[ ] Practice explaining how you would verify that registration, an order, or a profile update wrote the correct database records.

[ ] Save representative queries in your GitHub project under a sql-practice folder.

### Programming foundation for Playwright

Use JavaScript/TypeScript as the primary language because you are already learning Playwright. You do not need advanced algorithms, but you do need to understand your own test code.

[ ] Variables, strings, numbers, booleans, arrays, and objects.

[ ] Functions, parameters, return values, loops, conditions, and common array methods.

[ ] import/export modules, npm/package.json basics, and environment variables.

[ ] Promises and async/await well enough to explain why Playwright actions are awaited.

[ ] try/catch and basic error handling; read a stack trace from top to relevant application/test code.

[ ] Write 10-15 small exercises yourself rather than copying a course solution.

### Application target this week

[ ] Apply to 5-10 roles that are genuinely compatible with your level.

[ ] Record every application in a tracker.

[ ] Save the job description or key requirements so you can analyze skill patterns.

[ ] Do not reject yourself because a role asks for 1-2 years if most core requirements match; use judgment and apply when the role is plausibly junior.

## Week 5 (Oct 12-18): REST API Testing with Postman

Objective Prove that you can test services without depending on the user interface.

HTTP methods: GET, POST, PUT, PATCH, DELETE

Status codes: 2xx, 4xx, 5xx patterns

Headers and Content-Type

Path and query parameters

JSON request/response bodies

Authentication concepts

Positive and negative testing

Schema/data validation

Response-time awareness

Environment variables and collections

### Portfolio deliverable

[ ] Create approximately 20 API tests covering success and failure cases.

[ ] Add Postman tests/assertions for status codes and important response values.

[ ] Use variables for reusable values where possible.

[ ] Create at least one multi-step flow, for example create -> retrieve -> update -> delete.

[ ] Export the Postman collection and include instructions in the README.

### Application target

[ ] 10-15 targeted applications this week.

[ ] Begin using API testing as a keyword only after you can demonstrate it.

[ ] Note which roles repeatedly ask for Postman, REST, SQL, or automation.

## Week 6 (Oct 19-25): Playwright Fundamentals

Objective Turn your video knowledge into reliable tests that you can explain line by line.

### Must understand

test() and expect()

page and browser context

Locators: getByRole, getByLabel, getByText, getByTestId, CSS only when appropriate

Auto-waiting and why hard sleeps are usually a bad idea

Assertions and retry behavior

beforeEach and shared setup

Test data

Screenshots and traces

Running one test, one file, headed mode, debug mode

Basic configuration and projects/browsers

### Code and debugging requirements

[ ] Be able to write a small helper function and explain its inputs/outputs.

[ ] Be able to read an object/JSON response and access nested fields safely.

[ ] When a test fails, classify the likely cause: product defect, locator/timing issue, bad test data, environment issue, or assertion/test-code issue.

[ ] Keep a debugging log for at least three failures: symptom -> evidence -> root cause -> fix.

### Automate first

[ ] Valid login

[ ] Invalid login

[ ] Registration or account creation flow

[ ] Product search

[ ] Product detail verification

[ ] Add item to cart

[ ] Remove item from cart

[ ] Cart quantity or state check

[ ] Form validation

[ ] Logout

### Week 6 exit criteria

[ ] 8-12 tests run consistently on your machine.

[ ] No test depends on arbitrary long sleep calls to pass.

[ ] You can explain every locator and assertion you used.

[ ] You can debug a failure using Playwright output, trace, screenshot, or headed mode.

## Week 7 (Oct 26-Nov 1): Build a Maintainable Automation Project

Objective Make the repository look like deliberate QA engineering rather than copied tutorial files.

[ ] Grow to approximately 15-25 meaningful automated tests.

[ ] Introduce page objects only where they reduce duplication; do not create unnecessary abstraction.

[ ] Separate reusable test data from test logic where practical.

[ ] Use clear test names that describe behavior rather than implementation.

[ ] Tag or group smoke tests if useful.

[ ] Run tests in at least two browsers or explain why your selected scope uses one.

[ ] Practice intentionally breaking one test and diagnosing the failure.

### Application target

[ ] 15-20 targeted applications.

[ ] Start applying to some QA automation roles where the requirements are not clearly senior.

[ ] Do not make SDET the majority of your search if listings require strong production coding experience.

## Week 8 (Nov 2-8): GitHub, CI, and Portfolio Polish

Objective A recruiter or interviewer should understand the project within two minutes and be able to run it from your instructions.

[ ] Write a strong README: purpose, application under test, scope, tools, manual testing, API testing, automation structure, setup, commands, results, known limitations.

[ ] Add a GitHub Actions workflow to install dependencies and execute the Playwright suite.

[ ] Remove tutorial leftovers, unused code, secrets, credentials, duplicate screenshots, and broken tests.

[ ] Use meaningful commit messages.

[ ] Pin or feature the repository on your GitHub profile if appropriate.

[ ] Make sure the repository contains no fabricated company/client information.

### Independent mini-project: prove the skills transfer

The main Automation Exercise repository is useful, but practice sites can look tutorial-driven. Spend 1-2 focused days on a second unfamiliar public demo application or open-source web app. Do not look for a prewritten test-case list first.

[ ] Write a one-page risk/feature map after 20-30 minutes of exploration.

[ ] Create 10-15 original test scenarios and execute at least 8.

[ ] Write 1-3 observed defect/usability reports if you genuinely find them; do not invent defects.

[ ] Automate 3-5 critical flows in a small separate Playwright folder/repository.

[ ] Write a short README explaining what you chose to test, what you deliberately did not test, and what you would do with more time.

This mini-project is intentionally small. Its purpose is to prove independent QA thinking, not to create another 50-test portfolio.

## Week 9 (Nov 9-15): Resume, LinkedIn, and Application Ramp

Objective Package your actual work so a recruiter can quickly understand your value despite the lack of professional QA experience.

[ ] Rework the baseline resume using application/recruiter feedback. Maintain two truthful versions: (1) manual/hybrid QA emphasis and (2) automation-leaning QA emphasis. The facts stay identical; only ordering and emphasis change.

[ ] Refine LinkedIn headline and About section using the language that repeatedly appears in realistic target roles, without keyword stuffing or exaggerating experience.

[ ] Add the portfolio repository to LinkedIn Featured if available.

[ ] Prepare a 30-second introduction and a 90-second project explanation.

[ ] Reach a sustainable pace of approximately 25-40 carefully matched applications per week.

[ ] Send approximately 10 recruiter/networking messages per week.

## Week 10 (Nov 16-22): Interview Sprint and Gap Fixing

Objective Practice communicating your skills under interview conditions and fix the highest-impact weaknesses revealed by applications.

[ ] Do at least three mock interviews this week.

[ ] Practice testing an unfamiliar feature aloud using structured test categories.

[ ] Write SQL queries without autocomplete for common interview tasks.

[ ] Open Postman and demonstrate a positive and negative API test from scratch.

[ ] Open Playwright and explain one test, one failure, and one debugging approach.

[ ] Review every real interview question you receive and add it to your question bank.

[ ] Continue applications; do not pause the funnel while waiting for interview outcomes.

# 5. Complete Portfolio Project Specification

Recommended practice application: Automation Exercise. It provides common e-commerce workflows that are suitable for manual, API, and UI automation practice.

## Repository structure

qa-ecommerce-portfolio/
├── README.md
├── manual-testing/
│   ├── test-plan.md
│   ├── test-cases.xlsx
│   ├── smoke-suite.xlsx
│   ├── regression-suite.xlsx
│   └── bug-reports/
├── api-testing/
│   └── ecommerce-postman-collection.json
├── sql-practice/
│   └── qa-validation-queries.sql
├── tests/
│   ├── auth/
│   ├── products/
│   ├── cart/
│   └── checkout/
├── pages/
├── test-data/
├── playwright.config.ts
├── package.json
└── .github/workflows/playwright.yml

## Test plan sections

Purpose and objectives

Application/features in scope

Out-of-scope items

Test types

Test environment

Entry criteria

Exit criteria

Test data approach

Risks and assumptions

Deliverables

Defect reporting approach

## Manual test coverage target

| Area | Coverage ideas |
| --- | --- |
| Registration | Valid data, required fields, invalid email, password rules, duplicate account, field limits |
| Login/Logout | Valid/invalid login, blank data, case handling, session/logout behavior, error messages |
| Products/Search | Search results, no results, product details, navigation, data correctness |
| Cart | Add/remove, quantity, duplicate item behavior, totals, persistence where applicable |
| Checkout | Required fields, order flow, totals, state transitions, error handling |
| Forms/Contact | Required fields, invalid inputs, messages, attachments if supported |
| Account | Profile/account details, updates, deletion where supported |

## Sample test case

| Field | Example |
| --- | --- |
| ID | TC-LOGIN-004 |
| Scenario | Login with valid registered credentials |
| Preconditions | A valid account exists; user is logged out |
| Steps | 1. Open login page 2. Enter registered email 3. Enter valid password 4. Click Login |
| Test Data | Valid QA test account |
| Expected | User is authenticated and logged-in state is clearly visible |
| Actual | Complete during execution |
| Status | Pass / Fail |

## Sample bug report

| Field | Example |
| --- | --- |
| Title | Cart quantity accepts an invalid value after update |
| Environment | Chrome, current desktop environment |
| Preconditions | One product is already in the cart |
| Steps | 1. Open cart 2. Change quantity to an invalid value 3. Submit/update |
| Expected | Invalid quantity is rejected with clear validation |
| Actual | Record the exact observed behavior |
| Severity | Choose based on impact |
| Priority | Choose based on business urgency |
| Evidence | Screenshot/video + exact test data |

## API test coverage target

[ ] Happy-path GET request

[ ] Resource not found

[ ] Required parameter missing

[ ] Invalid parameter value

[ ] Valid POST/create

[ ] Invalid POST body

[ ] Authentication success/failure if available

[ ] Update using PUT/PATCH

[ ] Delete flow

[ ] Unsupported method

[ ] Response content checks

[ ] Basic response-time observation

## Playwright automation target

[ ] Authentication: valid and invalid login

[ ] Registration/account flow where stable

[ ] Product search and result assertion

[ ] Product detail verification

[ ] Add to cart

[ ] Remove from cart

[ ] Quantity/state validation

[ ] Form validation

[ ] Checkout or order flow where feasible

[ ] Logout

[ ] At least one data-driven or reusable setup example

[ ] Failure evidence through screenshot/trace

## Programming/debugging evidence

[ ] Include code you wrote and can explain: at least one helper, reusable test-data approach, and clear async/await usage.

[ ] Keep a short debugging-notes.md with 3 real automation failures you diagnosed and fixed.

[ ] Do not include generated boilerplate you cannot explain just to make the framework look larger.

## Definition of Done for the portfolio

[ ] A stranger can understand what was tested from the README.

[ ] Manual test cases have actual execution results, not only planned steps.

[ ] Bug reports are reproducible and do not pretend hypothetical examples are real defects.

[ ] Postman collection runs without private credentials or secrets.

[ ] Playwright tests are stable enough to rerun and use meaningful assertions.

[ ] Repository setup instructions work on a clean machine in principle.

[ ] CI workflow is visible and the latest run is not permanently broken.

[ ] You can explain every major artifact in an interview.

[ ] The independent mini-project demonstrates that you can test a second application without following the main project’s existing test-case ideas.

[ ] At least one artifact shows diagnostic thinking (Network/Console evidence or an automation debugging note), not only pass/fail results.

# 6. Resume, LinkedIn, and Career-Gap Positioning

## Timing: baseline first, optimization later

Build the first usable resume in Week 3 because applications begin in Week 4. Week 9 is when you optimize it from actual response data. Never wait until Week 9 to have a resume.

## Recommended one-page resume order

1. Name + contact information + GitHub/LinkedIn

2. QA-focused professional summary

3. Technical skills

4. QA portfolio project(s)

5. Education: Master's in Computer Science, 2018

6. Optional additional information only if relevant

## Sample professional summary

Resume summary example Computer Science master’s graduate transitioning into Software Quality Assurance with hands-on project experience in manual testing, REST API testing, SQL, and Playwright automation. Built an end-to-end e-commerce QA portfolio covering test design, defect reporting, Postman API validation, and automated browser testing. Seeking an entry-level QA Engineer / QA Analyst opportunity to contribute strong analytical and technical skills.

## Skills section - only list these after you can demonstrate them

| Category | Possible skills |
| --- | --- |
| Testing | Manual Testing, Functional Testing, Regression Testing, Smoke Testing, Exploratory Testing, Test Case Design, Defect Reporting |
| Automation | Playwright, TypeScript/JavaScript |
| API | Postman, REST API Testing, JSON, HTTP |
| Database | SQL |
| Tools | Git, GitHub, GitHub Actions |
| Process | Agile/Scrum, SDLC, STLC |
| Programming | JavaScript/TypeScript fundamentals, async/await, npm/package.json basics |
| Diagnostics | Browser DevTools, Network/Console inspection, debugging, stack-trace reading |

## Two resume versions, same facts

Manual/hybrid version: lead with test design, regression, defect reporting, API testing, and SQL; keep Playwright visible but secondary. Automation-leaning version: lead with Playwright, TypeScript/JavaScript, API testing, debugging, Git/CI, then manual QA. Do not change dates, titles, project scope, or experience claims between versions.

## Project bullet examples

Designed and executed 40+ functional, negative, smoke, and regression test cases for an e-commerce web application.

Documented reproducible defects with steps, expected vs. actual results, severity/priority, and supporting evidence.

Created REST API tests in Postman covering positive and negative scenarios, response validation, and multi-step CRUD-style workflows.

Built Playwright automated tests for authentication, product search, cart, and checkout-related workflows using stable locators and assertions.

Used SQL queries to practice backend data verification and relational joins.

Configured automated Playwright execution through GitHub Actions and documented project setup in GitHub.

## How to discuss the 2018-to-present gap

Use the truth about what you actually did during that period. Keep the explanation short, then move toward your current preparation. Do not invent employment.

Interview structure “I completed my master’s in Computer Science in 2018. [Brief truthful explanation of the period since then.] More recently, I have been focusing on software QA and building hands-on experience in manual testing, API testing, SQL, and Playwright automation. I built a complete QA portfolio project and I’m now looking for an opportunity to apply those skills professionally.”

## LinkedIn checklist

[ ] Headline focuses on the target role and current skills, not “unemployed” or “seeking anything.”

[ ] About section tells the transition story in 5-8 concise lines.

[ ] Skills match what you can actually demonstrate.

[ ] GitHub project is visible in Featured or Projects when possible.

[ ] Education is accurate.

[ ] Profile photo and basic contact settings are professional and current.

[ ] Do not claim “QA Engineer at [company]” for a personal project.

## Sample networking message

Short message Hi [Name], I’m transitioning into software QA after a Computer Science master’s and have been building hands-on experience with manual testing, API testing, SQL, and Playwright. I’m currently applying for entry-level QA roles and would be glad to connect. If you have any advice on what your team values in junior QA candidates, I’d appreciate it.

# 7. Job Search System

## Search titles

QA Engineer

Software QA Engineer

QA Analyst

Software Tester

Test Engineer

Junior QA Engineer

Associate QA Engineer

Quality Assurance Engineer - Software

Junior Automation QA / QA Automation Engineer (selectively)

## Weekly application ramp

| Phase | Applications/week | Purpose |
| --- | --- | --- |
| Week 4 | 5-10 | Learn what listings ask for; test the resume direction |
| Week 5 | 10-15 | Add API-based roles as skills become real |
| Week 6 | 15-20 | Use Playwright work in applications/interviews |
| Week 7 | 15-20 | Add selected automation roles |
| Week 8 | 20-30 | Portfolio is now recruiter-readable |
| Weeks 9+ | 25-40 | Sustainable targeted pace; maintain quality |

## Application tracker columns

Date

Company

Role

Location/work arrangement

Source/link

Key requirements

Resume version

Status

Contact/recruiter

Follow-up date

Interview notes

Reason for rejection/lesson

## Before applying, use this 60-second check

[ ] Is this actually a software QA/test role?

[ ] Is the seniority plausible for someone without professional QA experience?

[ ] Can I match most of the core skills, even if not every preferred skill?

[ ] Does the role require a domain qualification I clearly do not have?

[ ] Can I customize the top third of my resume to the posting without exaggerating?

[ ] Can I explain why my portfolio is relevant to this role?

[ ] Do I meet the role’s work-location and work-authorization/sponsorship constraints as stated?

## Target-role scorecard

Give each posting a fast score before spending time customizing: +2 if 0-2 years/entry language; +2 if core work matches your portfolio; +1 for manual+API/SQL; +1 for Playwright/JS/TS; +1 for contract/project-hire openness. Subtract 3 for Senior/Lead/Staff; subtract 3 for a hard 5+ years requirement; subtract 2 for heavy framework architecture/advanced coding ownership. Apply mainly to positive-score roles. This is a prioritization tool, not a hiring guarantee.

## Experience bridge: create legitimate external testing evidence

Starting around Week 4-5, optionally join a reputable crowdtesting network such as uTest or Testlio. These platforms currently offer freelance testing opportunities, but work invitations are not guaranteed. The goal is not to replace the main job search; it is to gain real externally reviewed testing tasks if opportunities match you.

[ ] Complete onboarding/training and keep records only of work you are allowed to discuss. Respect every NDA/confidentiality rule.

[ ] If you complete paid testing, describe it accurately as freelance/crowdtesting experience—not as full-time employment and not as employment by the client brand.

[ ] Never put confidential client names, screenshots, test data, or proprietary defects into your public GitHub portfolio.

[ ] If no paid tasks appear, continue the primary portfolio/application plan; availability on these networks varies.

## Networking routine

[ ] 10 thoughtful recruiter or professional messages per week.

[ ] 15-20 relevant new connections per week when appropriate.

[ ] Ask for insight or a conversation; do not open with a long demand for a referral.

[ ] Follow up once after approximately one week if appropriate, then move on.

## What to do after an application

[ ] Save the posting or key requirements because listings can disappear.

[ ] Prepare 2-3 reasons your project matches the role.

[ ] If contacted, reread the exact posting before the call.

[ ] After an interview, document every technical question while it is fresh.

[ ] Improve your portfolio only when the change addresses a recurring market signal; do not rebuild it after every rejection.

# 8. Interview Preparation System

## 30-second introduction

Template “I have a master’s in Computer Science and I’m transitioning into software QA. I’ve built hands-on experience through an end-to-end testing project where I designed manual test cases, documented defects, tested REST APIs with Postman, used SQL for data validation exercises, and automated key workflows with Playwright. I’m looking for an entry-level QA role where I can contribute that foundation and continue growing in automation.”

## Manual QA question bank

[ ] What is the difference between a test scenario and a test case?

[ ] Smoke vs. sanity vs. regression testing?

[ ] Severity vs. priority?

[ ] What makes a good bug report?

[ ] What would you do if a developer says “cannot reproduce”?

[ ] What is exploratory testing?

[ ] When would you stop testing?

[ ] How do you decide what to test first?

[ ] How would you test a login page?

[ ] How would you test a shopping cart or checkout flow?

[ ] What do you do when requirements are unclear?

[ ] How do you decide whether a failed test is a product defect, test-data problem, environment problem, or automation issue?

## API question bank

[ ] GET vs. POST

[ ] PUT vs. PATCH

[ ] 200 vs. 201 vs. 204

[ ] 400 vs. 401 vs. 403 vs. 404

[ ] What are headers?

[ ] What is JSON?

[ ] What is an API request body?

[ ] How do you test authentication?

[ ] What negative tests would you create for an endpoint?

[ ] How do you validate a response?

[ ] How would you test an API when the UI is not ready?

## Playwright question bank

[ ] Why Playwright?

[ ] What is a locator?

[ ] Why prefer user-facing locators such as getByRole when possible?

[ ] What is auto-waiting?

[ ] What is a browser context?

[ ] What are fixtures?

[ ] What is the difference between setup in beforeEach and a reusable fixture?

[ ] How do you debug a failing test?

[ ] How do you avoid flaky tests?

[ ] When would you use a page object?

[ ] How do you run only one test or one file?

[ ] What evidence does a trace provide?

## SQL question bank

[ ] Find all users with a particular status.

[ ] Count orders per customer.

[ ] Find duplicate email addresses.

[ ] Join users and orders.

[ ] Find rows that do not have a related record.

[ ] Sort results and return the latest records.

[ ] Explain INNER JOIN vs. LEFT JOIN.

[ ] Explain NULL behavior at a basic level.

## Programming and debugging question bank

[ ] Explain async/await in the context of a Playwright test.

[ ] Given an array of test data, loop through it or transform/filter it.

[ ] Read a small TypeScript/JavaScript function and explain what it returns.

[ ] What is the difference between a product defect and an automation defect?

[ ] A Playwright test passed yesterday and fails today. What evidence do you collect first?

[ ] What would you inspect in the browser Network tab when a UI action fails?

[ ] Explain one real test failure from your project, its root cause, and how you fixed it.

## A strong framework for “How would you test a login page?”

| Category | Examples |
| --- | --- |
| Core functional | Valid login, invalid credentials, blank fields, submit behavior |
| Input validation | Email format, min/max lengths, spaces, special characters, case sensitivity |
| Error handling | Useful messages, no leakage of sensitive details, consistent placement |
| Session/state | Stay signed in, logout, browser back, multiple tabs, timeout where relevant |
| Security awareness | Password masking, rate limiting/lockout concept, secure transport awareness |
| Usability/accessibility | Keyboard flow, labels, focus, screen sizes, clear feedback |
| Compatibility | Supported browsers/devices according to product requirements |
| Performance/reliability | Reasonable response, repeat attempts, backend failure behavior |

## Behavioral interview preparation

Use the STAR structure: Situation -> Task -> Action -> Result. Your examples can come from school, personal projects, volunteering, teamwork, or other real experiences; they do not need to be fabricated QA jobs.

[ ] A time you found and solved a difficult problem

[ ] A time you learned a tool quickly

[ ] A disagreement or feedback situation

[ ] A time you made a mistake and corrected it

[ ] A time you prioritized multiple tasks

[ ] A time you worked with incomplete information

## Mock interview routine

1. 10 minutes: introduction + career transition explanation.

2. 20 minutes: manual QA concepts and test-design exercise.

3. 15 minutes: SQL/API questions.

4. 15 minutes: Playwright project walkthrough.

5. 10 minutes: behavioral question.

6. 10 minutes: review weak answers and write better versions in your own words.

# 9. Progress Checkpoints and Troubleshooting

## Milestone checks

| Checkpoint | Question | Action if weak |
| --- | --- | --- |
| End Week 2 | Can design tests without copying tutorials? | If no: reduce new material and practice one feature deeply. |
| End Week 5 | Can test an API and explain why each assertion matters? | If no: repeat one CRUD-style flow until fluent. |
| End Week 7 | Can explain and debug your Playwright suite? | If no: stop adding tests; stabilize and understand existing ones. |
| End Week 8 | Can another person understand/run the repo from README? | If no: improve documentation before adding more technology. |
| After ~40-50 targeted applications | Are you getting recruiter screens? | If almost none: revisit resume targeting, keywords, role seniority, and application quality. |
| After several recruiter screens | Are you advancing to technical interviews? | If not: strengthen transition story, role fit, and project explanation. |
| After several technical interviews | Are the same technical gaps repeating? | If yes: create a focused one-week remediation plan for those exact gaps. |

Use thresholds as signals, not guarantees Job-search response rates vary by location, timing, work authorization, industry, and the specific market. The application numbers in this plan are practical feedback points, not promises of interviews or offers.

## Treat the funnel diagnostically

If you have very few screens after roughly 40-60 well-matched applications, fix targeting/resume before adding more technology. If recruiter screens happen but technical interviews do not, strengthen your transition story and role fit. If technical interviews happen but you repeatedly fail the same area, spend one focused week on that exact gap. If you reach final rounds, keep the application funnel active while improving communication and behavioral examples.

## Common problems and fixes

| Problem | Best response |
| --- | --- |
| I keep watching videos but cannot build alone. | Pause videos. Rebuild one small feature from a blank project, using documentation only when blocked. |
| My Playwright tests are flaky. | Remove hard waits, improve locators/assertions, isolate test data, inspect trace/screenshots, and reduce shared state. |
| I cannot find enough real bugs. | Do not fabricate. Use fewer real defects plus clearly labeled test-design examples. Quality matters more than reaching a number. |
| I am applying only to “Junior” titles and finding little. | Broaden to QA Engineer, QA Analyst, Software Tester, and Test Engineer while checking seniority in the description. |
| I feel underqualified because listings mention 2+ years. | Evaluate the whole posting. Apply selectively when duties and core skills are realistically entry-level; skip clearly senior ownership/leadership roles. |
| I receive interviews but freeze. | Practice aloud, not silently. Record yourself explaining the project and test an unfamiliar feature under a timer. |
| I want to learn another tool before applying. | Only add a tool if multiple target postings require it or it fills a demonstrated gap. Otherwise keep applying. |

# 10. What to Learn Later

After you are consistently applying and interviewing, add skills based on actual job descriptions. A reasonable second-stage sequence is:

1. Deeper JavaScript/TypeScript beyond the working QA level already required in this plan.

2. Selenium if it repeatedly appears in realistic target roles or you need to work with an existing Selenium codebase.

3. Python for QA if your saved postings show a sustained pattern of Python requirements. Use a market trigger: if roughly 30% or more of your realistic target roles over two weeks ask for Python, add a focused 7-day Python-for-QA module. Do not abandon your Playwright/TypeScript progress just because senior postings mention Python.

4. Mobile testing/Appium if you target mobile-heavy companies.

5. Performance testing (for example, JMeter or k6) when roles require it.

6. Docker and CI/CD depth after you are comfortable with basic GitHub Actions.

7. Cloud basics when the products you target are cloud-centric.

8. Domain knowledge (finance, healthcare, e-commerce, etc.) based on the companies you pursue.

# 11. Final Job-Ready Checklist

### Manual QA

[ ] I can create test scenarios from a feature description.

[ ] I can write clear test cases with expected results.

[ ] I understand smoke, sanity, regression, exploratory, boundary, and negative testing.

[ ] I can write a professional defect report.

### API

[ ] I can send GET/POST/PUT/PATCH/DELETE requests.

[ ] I understand common HTTP status codes.

[ ] I can validate JSON responses in Postman.

[ ] I can create positive and negative API tests.

### SQL

[ ] I can write SELECT/WHERE/ORDER BY queries.

[ ] I can use COUNT/GROUP BY.

[ ] I can use INNER JOIN and LEFT JOIN.

[ ] I can describe how SQL supports QA validation.

### Playwright

[ ] I can create and run tests from scratch.

[ ] I use stable locators and meaningful assertions.

[ ] I understand context, fixtures, setup, and basic configuration.

[ ] I can debug failures using traces/screenshots/headed mode.

### Programming / diagnostics

[ ] I can explain the JavaScript/TypeScript used in my Playwright tests, including async/await.

[ ] I can read a simple stack trace and investigate a failing request in browser DevTools.

[ ] I can describe three real automation failures I debugged and how I found the cause.

### Portfolio

[ ] README clearly explains the project.

[ ] Manual, API, SQL, and automation evidence is organized.

[ ] CI runs automated tests.

[ ] No secrets or fabricated experience are present.

[ ] I have a small second QA assessment that was created without copying the primary practice site’s published test ideas.

### Job search

[ ] One-page resume is ready.

[ ] LinkedIn is aligned to QA.

[ ] Application tracker is active.

[ ] I can explain the 2018-to-present timeline truthfully and briefly.

[ ] I can explain my project in 90 seconds.

### Interview

[ ] I can test a login page aloud.

[ ] I can answer core manual QA questions without notes.

[ ] I can demonstrate a Postman request and a Playwright test.

[ ] I can solve basic SQL interview tasks.

[ ] I have practiced behavioral questions using real examples.

When to consider yourself ready to apply You do not need every box checked before your first application. Start in Week 4. By the time most boxes are checked, your focus should already be on interviews and improving from real employer feedback.

# 12. Reference Resources

| Resource | Use it for | Link |
| --- | --- | --- |
| Automation Exercise | Practice application and API exercises | https://www.automationexercise.com/ |
| Playwright documentation | Official Playwright test, locator, assertion, fixture, and debugging documentation | https://playwright.dev/docs/intro |
| Postman Learning Center | Official API testing, collections, variables, and test scripting documentation | https://learning.postman.com/ |
| Git documentation | Official Git reference and learning material | https://git-scm.com/doc |
| GitHub Actions documentation | Official CI workflow documentation | https://docs.github.com/en/actions |
| uTest | Optional crowdtesting/freelance testing experience bridge; opportunities vary | https://www.utest.com/ |
| Testlio Freelancer Network | Optional curated freelance testing opportunities; onboarding and matching required | https://www.testlio.com/join-the-community |

Use official documentation as the default reference when you are building. Tutorials are useful for introductions, but documentation forces you to solve problems rather than copy someone else’s exact steps.

# Your First 48 Hours

Do this first Do not start another full QA course. Create the repository, choose the practice application, write your first 15 test scenarios, and commit them. The plan becomes useful only when artifacts start existing.

[ ] Create the qa-ecommerce-portfolio repository and the folder structure.

[ ] Read through the application as a user for 20-30 minutes without automating anything.

[ ] List the main features and risks.

[ ] Write 15 original test scenarios.

[ ] Choose five scenarios and turn them into detailed test cases.

[ ] Review QA fundamentals only when you need them to improve those test cases.

[ ] Save five realistic QA job descriptions and highlight recurring skills. Ignore senior-only requirements when deciding your initial learning priorities.

[ ] Create a rough one-page resume shell now (contact, summary placeholder, skills, project, education) so it can mature alongside the project instead of being started from zero later.

[ ] Commit the work with a clear message such as “Add initial manual QA scenarios and test cases.”